## R8549_EpleyGcock205H
2026-09-23
Start Time | End Time | Dur (hr) | Cum Dur (hr) | Desc | Phase | Com
06:00 | 06:15 | 0.25 | 0.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, PRE OPS | Conducted PTB on prepping pad & NU/ testing BOP stack. RU Support Equipment.
06:15 | 06:45 | 0.5 | 0.75 | LOCATION | POSTSTIM, PRE OPS | Start prepping pad for D/O OP's. Spotting in all services.
06:45 | 08:15 | 1.5 | 2.25 | BOP | POSTSTIM, PRE OPS | NU adaptor flange, single Type-81 BOP loaded w/ 2-7/8" pipe rams, flow cross w/ hydraulic & manual gate valves, double gate Type-81 BOP loaded w/ 2-7/8" rams over (1 set) shear/ blind rams, single Type-U BOP loaded w/ 2-7/8" pipe rams, annular and Washington head. Torque all studs to spec.
08:15 | 09:15 | 1 | 3.25 | BOP | POSTSTIM, PRE OPS | Function tested all BOP rams. Performed accumulator draw down test. Good test. Filled stack and pressure tested all rams ( 2-7/8" test sub) to a max of 4,500 PSI & low of 250 PSI for 5 min each. Good tests. Pressure tested annular ( 2-7/8" test sub) to a max of 2,500 PSI & low of 250 PSI for 5 min. Good tests.
09:15 | 11:00 | 1.75 | 5 | LOCATION | POSTSTIM, PRE OPS | Continued prepping pad for D/O OP's. RU Flowback, Mixing plant, Sandcat and Centrifuge, Flarestack.
11:00 | 11:15 | 0.25 | 5.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, PRE OPS | Crew conducted PTB over Spotting in Rig and Equipment, RU pumps.
11:15 | 14:15 | 3 | 8.25 | RIG UP OR RIG DOWN | POSTSTIM, PRE OPS | MIRU Ranger 8549 pumps and support equipment. Spotted in Rig. NOTE: Tested E-kill on rig & laydown machine. Good test.
14:15 | 14:30 | 0.25 | 8.5 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, PRE OPS | Crew conducted PTB over Stand Rig, Secure and RU Floor.
14:30 | 16:30 | 2 | 10.5 | RIG UP OR RIG DOWN | POSTSTIM, PRE OPS | RU Ranger 8549 rig, floor and handling equipment.
16:30 | 20:45 | 4.25 | 14.75 | RIG UP OR RIG DOWN | POSTSTIM, PRE OPS | Racked, tallied & drifted WS. Continued prepping pad for D/O Op's.
20:45 | 21:00 | 0.25 | 15 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, PRE OPS | Crew conducted PTB over MU BHA & RIH w/ WS. Verified COFO operating properly & correct elevators utilized.
21:00 | 21:15 | 0.25 | 15.25 | BHA | POSTSTIM, PRE OPS | Measured & MU BHA #1, torque all connections to spec. NOTE BHA: 4-5/8" Varel SlipXtreme cone bit, bit sub, dual back pressure valve float sub w/ back pressure valves installed & V&V'd float direction, "R" PN on top 1st JT 2-7/8" & every 250 JTS there after.
21:15 | 01:45 | 4.5 | 19.75 | RUN IN HOLE | POSTSTIM, TRIP IN HOLE | RIH w/ BHA #1 & 275 JTS 2-7/8" FSS leaving EOT @ 8,667'. NOTE: V&V'd COFO operating properly. Loaded TBG every 50 JTS. Torque all 2-7/8" connections to 6,000 FT/LBS.
01:45 | 02:00 | 0.25 | 20 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, TRIP IN HOLE | Crew conducted PTB over RU power swivel and drilling plugs.
02:00 | 03:30 | 1.5 | 21.5 | SWIVEL | POSTSTIM, TRIP IN HOLE | MIRU XK-150 power swivel & equip. NOTE: V&V'd COFO operating properly.
03:30 | 06:00 | 2.5 | 24 | CIRCULATE | POSTSTIM, DRL OUT | Broke circulation, shut upper pipe rams, tested E-kills & kick outs on both pumps then tested surface lines w/ a low of 250 PSI and a high of 3,500 PSI. Bled down to 2,500 PSI and tested dual BPV's. Good test!
2026-09-24
Start Time | End Time | Dur (hr) | Cum Dur (hr) | Desc | Phase | Com
06:00 | 10:45 | 4.75 | 4.75 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 8725.73' - 10598.94' (Plug #51-#42), DO in 6 Min @ 4.0 BPM, return rate @ 3.8 BPM, Circ press 1195 psig, & WH press 228 psig. 22 min wash time. Comments #46 Sent 10bbl Dyed fresh water marker @ 8:54, Returned @ 9:45.
10:45 | 13:15 | 2.5 | 7.25 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 10808.88' - 11214.96' (Plug #41-#39), DO in 8 Min @ 4.0 BPM, return rate @ 2.7 BPM, Circ press 1167 psig, & WH press 133 psig. 20 min wash time. Comments #41 Sent 10bbl Dyed fresh water marker @ 11:25, Returned on time @ 12:28 .; #40 Sent 10bbl Dyed fresh water marker @ 11:25, Returned on time @ 13:16 .
13:15 | 18:00 | 4.75 | 12 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 11416.71' - 12834.73' (Plug #38-#31), DO in 6 Min @ 4.0 BPM, return rate @ 4.0 BPM, Circ press 1219 psig, & WH press 126 psig. 21 min wash time. Comments #38 Sent 10bbl, 93# Liquid Diverter pill @ 14:19, on surface @ 15:46. On time.; #32 CWC on top plug 31 on JT 407 through shift change. Sent 10 BBLS FW BLUE dyed marker @16:48, ETA @ 17:50. Marker on surface @ 17:47. On time.; #31 Changed SS JT 407.
18:00 | 23:00 | 5 | 17 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 13039.56' - 14464.29' (Plug #30-#23), DO in 8 Min @ 4.3 BPM, return rate @ 4.5 BPM, Circ press 1450 psig, & WH press 221 psig. 25 min wash time. Comments #27 10 BBLS FW BLUE dyed marker sent @ 20:24, ETA @ 21:30. Marker on surface @ 21:46. On time.
23:00 | 03:30 | 4.5 | 21.5 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 14671.42' - 15888.63' (Plug #22-#16), DO in 8 Min @ 4.5 BPM, return rate @ 4.6 BPM, Circ press 1643 psig, & WH press 161 psig. 20 min wash time. Comments #22 10 BBLS FW BLUE dyed marker sent @ 23:40, ETA @ 01:05. Marker on surface @ 01:16. On time.; #17 CWC on top plug 16 on JT 504. Sent 10 BBLS FW BLUE dyed marker sent @ 01:56, ETA @ 03:05. Marker on surface @ 3:24. On time.
03:30 | 06:00 | 2.5 | 24 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 16101.04' - 16913.39' (Plug #15-#11), DO in 6 Min @ 4.5 BPM, return rate @ 4.4 BPM, Circ press 1840 psig, & WH press 171 psig. 23 min wash time. Comments #12 CWC on top of plug 11 for Crew Change
2026-09-25
Start Time | End Time | Dur (hr) | Cum Dur (hr) | Desc | Phase | Com
06:00 | 06:30 | 0.5 | 0.5 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 16913.39' (Plug #11), DO in 4 Min @ 4.5 BPM, return rate @ 4.3 BPM, Circ press 1900 psig, & WH press 180 psig. 20 min wash time. Comments
06:30 | 07:30 | 1 | 1.5 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 17146.91' (Plug #10), DO in 3 Min @ 4.5 BPM, return rate @ 4.2 BPM, Circ press 1900 psig, & WH press 180 psig. 21 min wash time. Comments #10 CWC for 15 mins then change out washington rubber.
07:30 | 09:15 | 1.75 | 3.25 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 17335.54' - 17537.38' (Plug #9-#8), DO in 5 Min @ 4.5 BPM, return rate @ 4.2 BPM, Circ press 1900 psig, & WH press 220 psig. 33 min wash time. Comments #8 Changed SS on joint 554.
09:15 | 12:00 | 2.75 | 6 | DRILL OUT PLUG | POSTSTIM, DRL OUT | RIH to Depth 17730.85' - 18726.85' (Plug #7-#2), DO in 5 Min @ 4.5 BPM, return rate @ 4.4 BPM, Circ press 1900 psig, & WH press 235 psig. 22 min wash time. Comments
12:00 | 16:15 | 4.25 | 10.25 | CIRCULATE | POSTSTIM, DRL OUT | CWC, displaced Aprhron & spotted breaker in lateral on top of plug 1 @ 18,783' on JT 597. 1st marker sent @ 11:59, marker on surface @ 13:22 (On Time). 2nd marker sent @ 12:32, marker on surface @ 13:54 (On time). PR: 4.5 BPM @ 1,900 PSI, RR: 4.5 BPM @ 290 PSI Torque: 120 RPM's @ 3,50000 FT/LBS Good plug parts, Heavy sand, no gas. PU: 75K LBS S/O: 50K LBS
16:15 | 16:30 | 0.25 | 10.5 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, DRL OUT | Crew conducted PTB over RD swivel.
16:30 | 18:00 | 1.5 | 12 | RIG UP OR RIG DOWN | POSTSTIM, DRL OUT | RD XK-150 power swivel & equip. Made rig ready to POOH w/ 2-7/8 WS. PU @ 94K LBS, SICP- 430 PSI.
18:00 | 18:30 | 0.5 | 12.5 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, TRIP OUT OF HOLE | Crew conducted PTB over POOH laying down WS.
18:30 | 05:15 | 10.75 | 23.25 | PULL OUT OF HOLE | POSTSTIM, TRIP OUT OF HOLE | POOH laying down w/ 18,783' WS (597 JTS FSS). Stop w/ 100 JTS in the hole, leaving EOT 3,165' & killed well on the w/ 20 BBLS 10# BW down TBG followed by 200 BBLS 10# BW down CSG. Capped kill w/ 15 BBLS 11.6# CaCl2 down TBG followed by 45 BBLS 11.6# CaChl2 down CSG. SICP 0 PSI. NOTE: Verified COFO operating properly before POOH.
05:15 | 05:30 | 0.25 | 23.5 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, SET PROD | Crew conducted PTB over flushing wellbore.
05:30 | 06:00 | 0.5 | 24 | FLUSH | POSTSTIM, SET PROD | Cycled then flushed BOP stack, surface iron & both "B" section wheel vavles w/ 5 BBLS FW each.
2026-09-26
Start Time | End Time | Dur (hr) | Cum Dur (hr) | Desc | Phase | Com
06:00 | 07:15 | 1.25 | 1.25 | FLUSH | POSTSTIM, SET PROD | Flushed wellbore w/ 210 BBLS FW. SICP - 660 PSI
07:15 | 07:30 | 0.25 | 1.5 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, SET PROD | Conducted PTB over lower rig floor and Remove washington head.
07:30 | 08:15 | 0.75 | 2.25 | WORKOVER RIG | POSTSTIM, SET PROD | Change over handling equipment, Lower rig floor and remove washington head. Prep rig to RU Wireline unit.
08:15 | 08:30 | 0.25 | 2.5 | WIRELINE | POSTSTIM, SET PROD | Conducted PTB over MIRU wireline w/ equipemnt & wireline OP's.
08:30 | 17:00 | 8.5 | 11 | PACKER | POSTSTIM, SET PROD | MIRU Renegade wireline truck & equipment RIH w/ 4.50" GR/JB & weight bar to 8,450' KB. ( Correlated depth w/ CSG marker JT @ 8,182' - 8,202') POOH w/ same. Flushed wellbore w/ 210 BBLS FW based Imperative ESP chemical landing package. (SICP- 680 PSI). RIH & set Tryton ESP catch w/ top @ 8,354' KB. POOH w/ setting tool. Performed negative PSI test for 30 MIN., Good test. RD & MOL Renegade wireline truck& equipment. NOTE: Set catch w/ 3 pins in pump out plug (each pin 424 PSI/ pin), SI CSG Pressure 650 PSI. Anticipated pump out pressure ~1,952 PSI.
17:00 | 17:15 | 0.25 | 11.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, SET PROD | Crew conducted PTB over RU spoolers, MU ESP & RIH w/ production TBG.
17:15 | 17:30 | 0.25 | 11.5 | RUN PRODUCTION | POSTSTIM, SET PROD | Racked, tallied & drifted 2-7/8” 6.5# L-80, IPC (TIC-20AR internal coating) production TBG. Drifted BOP stack w/ TBG hanger. MIRU Innovex #2 ESP cable, FlowCo CT line spoolers w/ sheaves & ESP equipment trailer.
17:30 | 23:00 | 5.5 | 17 | PRODUCTION TUBING | POSTSTIM, SET PROD | RIH w/ bull plug & 8 JTS 2-7/8" L-80, EUE, 6.5# production TBG (as tail pipe/ mud JTS). MU Baker ESP equipment.
23:00 | 23:15 | 0.25 | 17.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, SET PROD | Crew conducted PTB over RIH w/ production TBG.
23:15 | 06:00 | 6.75 | 24 | PRODUCTION TUBING | POSTSTIM, SET PROD | RIH w/ Baker ESP & 240 JTS 2-7/8” 6.5# L-80, IPC (TIC-20AR internal coating) production TBG. NOTE: Installed HULK clamps on ESP MLE & from ESP up to ~2,600' from surface ( 7 MLE & 160 on TBG string). Banded #2 ESP cable & CT line w/ 4 bands per JT. Torque all 2-7/8" L-80 6.5# EUE TBG connections to 2,250 FT/LBS. Ran a total of 248 JTS TBG including IPC & tail pipe/ mud JTS.
2026-09-27
Start Time | End Time | Dur (hr) | Cum Dur (hr) | Desc | Phase | Com
06:00 | 06:15 | 0.25 | 0.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, SET PROD | Crew conducted PTB covering lowering sheaves & landing hanger.
06:15 | 08:00 | 1.75 | 2 | PRODUCTION TUBING | POSTSTIM, SET PROD | MU tubing hanger with back pressure check valve. Lowered sheaves. Installed 1/4" CT & ESP cable through hanger. Landed hanger, leaving sensor @ 8,049' & EOT @ 8,316' KB. Landing Weight - 58k lbs.
08:00 | 08:15 | 0.25 | 2.25 | NON ACTIVE DUE TO SAFETY EVENT | POSTSTIM, POST OPS | Crew conducted PTB over RD rig rig floor & rig.
08:15 | 08:30 | 0.25 | 2.5 | RUN PRODUCTION | POSTSTIM, POST OPS | RD TBG handling equipment, rig floor & support equipment. RDMO Rig.
08:30 | 10:30 | 2 | 4.5 | BOP | POSTSTIM, POST OPS | ND BOP stack & flow cross.
10:30 | 11:15 | 0.75 | 5.25 | PRODUCTION TREE | POSTSTIM, POST OPS | NU prod tree w/ ESP penetrator & CT line. Filled flange void w/ oil and tested hanger seals to 5,000 PSI. Good test!
11:15 | 11:45 | 0.5 | 5.75 | WELLHEAD | POSTSTIM, POST OPS | Shell tested production tree & both "B" section (CSG) valves to 250 PSI low & 4,500 PSI high for 5 min each. Good test! Lube out two-way check valve w/ lubricator.
11:45 | 12:15 | 0.5 | 6.25 | FLUSH | POSTSTIM, POST OPS | Burst POP, Plug bust @ 1980psi, flush 20bbls past plug. SICP 600psi. TOTP FINAL REPORT